APURVI INDUSTRIES

US + UK SEO Master Plan

400,000 Search Impressions in 30 Days  —  SEO & Marketing Team Brief

Prepared for: SEO Team & Marketing

Date: 29 June 2026  ·  Target geos: United States + United Kingdom

Compiled from 6 parallel deep-research agents covering keywords, content, authority/links, technical/AI search, competitor teardown, and impressions math.

# 1. Executive Summary

Apurvi Industries is launching a 30-day US + UK SEO push targeting 400,000 search impressions. This brief is the SEO and marketing team's complete playbook: keywords to target, content to publish, links to acquire, paid campaigns to launch, and a day-by-day calendar. The tech team has a parallel brief covering on-site code changes — work in lock-step with them.

Brutal-honest verdict: 400K from pure organic in 30 days is impossible for a new US/UK entrant. 400K hybrid (organic + AI search + community + ~$8–10K paid) is achievable. The smarter target is 250–400K impressions and 30 qualified RFQs in month 1, then scale to 600K–1M in months 2–3 as organic compounds.

## Apurvi's unfair advantages in 2026

Section 232 tariffs — Trump's April 6, 2026 proclamation raised Section 232 to 50% on Chinese stainless. US procurement teams are urgently searching for non-Chinese suppliers right now.

UK CBAM phase-in — Forces European buyers to verify origin and carbon credentials. EN 10204 3.1 MTC — which Apurvi already issues — is now mandatory.

Aluminum vapour recovery tubing — Fewer than 5 manufacturers globally serve this niche. Near-monopoly opportunity.

Real Mehsana plant + ISO 9001:2015 + 25–200 HP coverage — Unbeatable E-E-A-T versus paper-thin competitors.

AI search timing — Google AI Overviews and Bing Copilot now appear in 35–40% of US/UK B2B queries. No Indian competitor is doing AEO well — Apurvi can own this for 6–12 months.

## Impression-build formula (30-day total)

| Layer | 30-day impressions | Effort | Cost |
| --- | --- | --- | --- |
| Organic (long-tail + brand) | 65–130K | 20 new pages + on-site fixes | Time only |
| AI search citations (AIO / Perplexity / ChatGPT / Bing Copilot) | 15–30K | AEO content + llms.txt | Time only |
| LinkedIn organic (founder + company) | 30–100K | 5 posts/week + 1 newsletter | Time only |
| Reddit + Quora organic | 20–80K | 3–5 posts/week | Time only |
| YouTube organic (factory shorts) | 5–20K | 4–6 videos | Phone + 4 hrs/video |
| Pinterest + niche directories | 5–15K | 30 pins + profile claims | 8 hrs total |
| Paid (Google + Bing + LinkedIn + Reddit + YouTube + Display + Quora) | 200–300K | Campaign setup + mgmt | ~$8–10K |
| TOTAL | ~420K (range 340–675K) |  | $8–10K |

# 2. Top 30 US + UK Keywords to Target

Volumes are monthly. KD = Keyword Difficulty (0–100). Source: blended estimates from Google Keyword Planner banding, Ahrefs/SEMrush public data, expert reasoning.

| # | Keyword | US Vol | UK Vol | KD | Target page |
| --- | --- | --- | --- | --- | --- |
| 1 | stainless steel pipe suppliers | 2,400 | 880 | 58 | /us/ or /uk/ homepage |
| 2 | ASTM A312 pipe supplier | 590 | 110 | 32 | /us/astm-a312-tp304-stainless-steel-pipe-supplier |
| 3 | ASTM A312 TP304 seamless pipe | 480 | 90 | 28 | same as above |
| 4 | ASTM A268 stainless tube | 320 | 70 | 18 | /us/astm-a268-stainless-steel-tubing-manufacturer |
| 5 | stainless steel motor shell tube | 90 | 40 | 12 | /us/submersible-pump-motor-shell-tube-supplier (HERO) |
| 6 | submersible pump motor housing tube | 170 | 70 | 14 | same as above |
| 7 | EN 10296 welded stainless tube | 210 | 320 | 24 | /uk/en-10296-2-welded-stainless-steel-tube-supplier |
| 8 | EN 10204 3.1 MTC supplier | 140 | 260 | 22 | /uk/en-10204-3-1-mtc-stainless-pipe-manufacturer |
| 9 | stainless steel pipe wholesaler USA | 320 | — | 36 | /us/ |
| 10 | stainless steel tube manufacturer India | 880 | 390 | 41 | /company → /us/about-us-and-export |
| 11 | SS 304 vs 316 | 6,600 | 2,400 | 26 | Extend existing blog with US/UK angle |
| 12 | ASTM A312 vs A213 | 590 | 170 | 14 | New blog (quick-win) |
| 13 | aluminum vapor recovery tubing | 90 | — | 8 | /us/aluminum-vapor-recovery-tubing-stage-i-retrofit (HERO) |
| 14 | aluminium vapour recovery pipe | — | 70 | 6 | /uk/aluminium-vapour-recovery-tubing |
| 15 | EPA Stage II vapor recovery piping | 260 | — | 22 | /us/aluminum-vapor-recovery-tubing-stage-i-retrofit |
| 16 | 6061 aluminum tubing supplier | 720 | 140 | 38 | /us/aluminum-vapor-recovery-tubing |
| 17 | 6063 aluminium tube UK | 50 | 210 | 18 | /uk/aluminium-vapour-recovery-tubing |
| 18 | precision aluminium tubing UK | 90 | 480 | 28 | /uk/precision-aluminium-tubing |
| 19 | borehole pump tube supplier | 30 | 170 | 12 | /uk/borehole-pump-tube-supplier |
| 20 | submersible pump pipe manufacturer | 480 | 90 | 30 | /us/submersible-pump-motor-shell-tube-supplier |
| 21 | NRV pipe stainless steel | 110 | 90 | 14 | /products#pump-pipe-nrv |
| 22 | 25 HP submersible pump tube | 40 | 20 | 6 | /us/high-hp-submersible-motor-tube |
| 23 | 100 HP submersible motor tube manufacturer | 30 | 10 | 4 | same as above |
| 24 | stainless steel tube for OEM | 170 | 90 | 22 | /us/stainless-steel-tube-for-oem |
| 25 | seamless stainless steel pipe USA | 590 | — | 44 | /us/ |
| 26 | ISO 9001 stainless tube supplier | 110 | 70 | 16 | /quality-certifications |
| 27 | ground OD ID stainless tube | 50 | 30 | 8 | /products#pressure-pump-sleeve |
| 28 | pump shaft sleeve tubing 316L | 70 | 30 | 10 | /products#pressure-pump-sleeve |
| 29 | long stainless steel tube 6m | 40 | 30 | 6 | /products#manufacturing-long-tube |
| 30 | deep well submersible motor tube | 90 | 40 | 8 | /us/high-hp-submersible-motor-tube |

## 10 quick-win keywords (rank top-10 in < 60 days)

Long-tail B2B queries no Western competitor owns. Each gets a 700–1,200 word landing page with the exact keyword in H1, slug, and first 100 words.

stainless steel motor tube manufacturer for OEM submersible pumps (KD 3)

EN 10204 3.1 MTC stainless steel motor tube (KD 4)

aluminum vapour recovery tubing manufacturer India (KD 2)

ASTM A268 TP409 motor shell tube supplier (KD 3)

25 HP to 200 HP submersible pump tube (KD 3)

ground OD ID stainless tube for pump sleeve (KD 2)

6063-T6 aluminium vapour tubing UK (KD 4)

ASTM A312 TP316L motor tube wholesale price (KD 6)

submersible pump pipe with NRV thread (KD 3)

precision stainless steel tube 2 inch to 12 inch OD (KD 5)

## US vs UK spelling rules — CRITICAL

Why this matters: Apurvi currently writes 'Aluminum Vapour Tubing' — a hybrid that ranks for neither market. Every /us/ page must use US spelling; every /uk/ page must use UK spelling.

| Concept | US spelling | UK spelling |
| --- | --- | --- |
| Metal | aluminum | aluminium |
| Vapor | vapor | vapour |
| Borewell / water well / borehole | water well | borehole |
| Pump pipe / pump tube | pump pipe | pump tube / tubing |
| Catalog / catalogue | catalog | catalogue |

# 3. Content Architecture — 3 Pillars × 8 Clusters = 27 New Pages

Each pillar is ~3,500 words. Each cluster is ~1,500–2,500 words. Every cluster links UP to its pillar and SIDEWAYS to 2 sibling clusters.

## PILLAR A — Stainless Steel Motor Tubes for Submersible Pumps (US/UK Buyer's Guide)

A1 — 304L vs 316L for submersible motor housings (saltwater/freshwater decision tree)

A2 — 4″ vs 6″ vs 8″ motor tube sizing — HP / GPM / depth mapping

A3 — ASTM A312 vs A213 — which standard your pump motor tube actually needs

A4 — Wall thickness selection: pressure rating + collapse depth calc

A5 — Welded vs seamless motor tubes — UL/NSF pump assembler acceptance criteria

A6 — Pickling, passivation & 0.4 Ra ID finish — why ID finish kills pump life

A7 — Higher HP (25–200 HP) deep-well motor tube — long-tube manufacturing explained

A8 — Avoiding pitting corrosion in coastal US/UK groundwater — chloride field data

## PILLAR B — Aluminum Vapour Recovery Tubing for Gas Stations (EPA + UK PPC)

B1 — Al 6061 vs 6063 vs 5052 — alloy for vapour recovery lines

B2 — Stage II decommissioning in the US — what tubing you keep vs replace

B3 — UK PPC permits + vapour recovery — new-build material spec

B4 — EN 754 vs ASTM B210 for aluminum drawn tubing — cross-reference

B5 — Forecourt fire-safety + aluminum tubing weld practices

B6 — Replacing copper vapour lines with aluminum — TCO calculator

B7 — Sourcing aluminum vapour tubing from India — HS codes 7608, lead times

B8 — UL/ETV listing pathway for imported aluminum tubing

## PILLAR C — Sourcing SS Pipe from India: Risk-Free Procurement Playbook

C1 — EN 10204 Type 3.1 MTC — how to read it (annotated sample)

C2 — ISO 9001:2015 + IS:6761 audit checklist before signing an Indian supplier

C3 — SS 202 vs 304 vs 316 — buyer downgrade traps

C4 — Incoterms: CIF vs FOB to US East Coast / UK Felixstowe

C5 — US Section 232 + UK CBAM on Indian SS — 2026 landed-cost reality

C6 — Third-party inspection (SGS/TUV/BV) — when it pays back

C7 — SS pressure pump sleeves + NRV pipe — buyer spec template

C8 — ASTM A312 mill traceability — heat number → MTC → invoice chain

## 20 blog post titles, ranked by ROI

| # | Title | Target keyword | Words | CTA |
| --- | --- | --- | --- | --- |
| 1 | SS 304 vs 316 for Submersible Pump Motor Tubes: 2026 Engineer's Decision Guide | ss 304 vs 316 submersible pump | 2,200 | MTC sample PDF |
| 2 | ASTM A312 vs A213 vs A268: Which Stainless Tube Standard Your Project Needs | astm a312 vs a213 | 2,000 | Spec sheet bundle |
| 3 | EN 10204 Type 3.1 Mill Test Certificate Explained (with Annotated Sample) | en 10204 3.1 mtc | 1,800 | Download annotated MTC |
| 4 | 4″ vs 6″ vs 8″ Submersible Motor Tube Sizing Chart (HP / GPM / Depth) | submersible motor tube sizing | 2,400 | Sizing calculator |
| 5 | Stage II Vapour Recovery Decommissioning: Which Aluminum Tubing You Keep | stage ii vapor recovery decommissioning | 2,200 | RFQ + EPA checklist |
| 6 | Al 6061 vs 6063 vs 5052 for Petrol Vapour Lines: Corrosion + Formability Compared | al 6061 vs 6063 vs 5052 | 1,900 | Material data PDF |
| 7 | Sourcing Stainless Steel Pipes from India: 12-Point Audit Before You Sign | sourcing stainless steel from india | 2,500 | Supplier audit checklist |
| 8 | UK PPC Vapour Recovery Compliance: Material Specs for New Service Stations | uk ppc vapour recovery | 1,800 | RFQ + UK spec sheet |
| 9 | Higher HP Deep-Well Motor Tubes (15–50 HP): Long-Tube Manufacturing Matters | high hp submersible motor tube | 1,600 | Plant tour + RFQ |
| 10 | How to Spot a Fake Mill Test Certificate (5 Red Flags Buyers Miss) | fake mill test certificate | 1,700 | MTC verification call |
| 11 | SS Pressure Pump Sleeve Spec Sheet: NRV Pipe Dimensions & Tolerances | ss pressure pump sleeve | 1,500 | Spec sheet bundle |
| 12 | Section 232 Tariffs & CBAM 2026: Real Landed Cost of Indian SS Pipe in US/UK | section 232 stainless steel india 2026 | 2,000 | Landed-cost calculator |
| 13 | Pickling vs Passivation vs Electropolishing: What Your Pump Tube ID Finish Should Be | passivation vs pickling stainless tube | 1,800 | Finish comparison PDF |
| 14 | Pitting Corrosion in Coastal Submersible Pumps: 304L vs 316L Field Data | pitting corrosion submersible pump | 1,600 | Case study PDF |
| 15 | ISO 9001:2015 + IS:6761 Combined Audit: What US/UK Importers Should Check | iso 9001 is 6761 audit | 1,400 | Audit checklist |
| 16 | Wall Thickness & Collapse Pressure for Submersible Motor Tubes (Working Formulas) | submersible motor tube wall thickness | 1,700 | Calculator + tables |
| 17 | EN 754 vs ASTM B210: Cross-Reference Table for Aluminum Drawn Tubing Buyers | en 754 vs astm b210 | 1,300 | Cross-ref PDF |
| 18 | CIF vs FOB for Stainless Pipe Shipments to US/UK: Hidden Cost Breakdown | cif vs fob stainless steel pipe india | 1,500 | Incoterm cheatsheet |
| 19 | Welded vs Seamless Motor Tubes: When UL/NSF Pump Builders Accept Each | welded vs seamless motor tube | 1,600 | UL/NSF reference |
| 20 | Replacing Copper Vapour Lines With Aluminum: 10-Year TCO for Fuel Retailers | aluminum vapor recovery tco | 1,500 | TCO calculator |

## 10 lead magnets, ranked by impression-driving potential

Pump-Tube Sizing Calculator (interactive JS, embeddable — every embed = backlink)

EN 10204 3.1 MTC Annotated Sample PDF (real Apurvi MTC with arrows)

ASTM A312 vs A213 vs A268 Interactive Comparison Tool

Gas-Station Vapour Recovery Compliance Map (US EPA Stage II by state + UK PPC)

Indian SS Pipe Landed-Cost Calculator (Section 232 + CBAM baked in)

Submersible Motor Tube Spec Sheet Bundle (8 PDFs, gated by email)

12-Point Indian Supplier Audit Checklist (Word doc)

Wall Thickness / Collapse Pressure Workbook (Excel)

Pitting Corrosion Field Study — Apurvi's original chloride exposure data (12 pp whitepaper)

Cross-Reference Card: EN 10296 ↔ ASTM A312 ↔ IS:6761 ↔ JIS G3463 (printable A3)

# 4. Authority & Link Building

Sliding scale: 5–10 DA 60+ links = bare-minimum signal; 20–30 links = long-tail ranking shifts; 50–80 links = mid-tail movement.

## Tier 1 — Must-do directories (Week 1)

| # | Directory | Country | DA | Type | Why |
| --- | --- | --- | --- | --- | --- |
| 1 | ThomasNet | US | 86 | Free + paid premium | CRITICAL — #1 US industrial buyer search |
| 2 | GlobalSpec / Engineering360 | US/Global | 85 | Free supplier profile | IEEE-engineer audience |
| 3 | Kompass UK | UK | 79 | Free + Booster | Indexed in 26 languages |
| 4 | Kompass Global / US | US | 79 | Free company page | Same authority, US subdir |
| 5 | Europages | EU | 77 | Free + premium | 2.6M companies, 6M monthly searches |
| 6 | Applegate Marketplace UK | UK | 64 | Free + RFQ matching | UK's longest-established |
| 7 | DirectIndustry (VirtualExpo) | EU/Global | 72 | Paid | Product page indexing |
| 8 | Manta | US | 72 | Free claim | US small/mid B2B |
| 9 | D&B Hoovers / Dun & Bradstreet | US | 91 | Free DUNS + paid | Required for US gov contracts |
| 10 | MFG.com | US | 60 | Free + RFQ bidding | Active RFQs for SS shops |
| 11 | IndustryNet | US | 58 | Free | US-focused |
| 12 | MacRAE'S Blue Book | US | 60 | Free basic | Long-running US industrial |
| 13 | Yell.com | UK | 76 | Free + paid | UK local + B2B trust |
| 14 | AZoM Materials | Global | 73 | Supplier profile | Engineering audience |
| 15 | Stainless Steel World Directory | NL/Global | 55 | Paid niche | Direct keyword relevance |

## Tier 2 — 20 industry publications to pitch

Pumps & Systems Magazine (US) — pumpsandsystems.com/editorial — technical contributed articles

WaterWorld Magazine (US) — waterworld.com/magazine — tech articles + supplier insights

Flow Control Magazine (US) — flowcontrolnetwork.com — guest tech articles

Process Industry Forum (UK) — processindustryforum.com — guest posts, supplier news

The Engineer (UK) — theengineer.co.uk — news + opinion

Eureka Magazine (UK) — eurekamagazine.co.uk — design engineering

Petrol Plaza (EU/UK) — petrolplaza.com — industry interviews

CSP Daily News (US) — cspdailynews.com/fuels — industry features

Fuels Market News (US) — fuelsmarketnews.com — op-eds, supplier features

NACE / AMPP Materials Performance — ampp.org/publications — technical articles

Hydrocarbon Engineering (UK) — hydrocarbonengineering.com — tech features

Stainless Steel World (NL) — stainless-steel-world.net — articles + directory

World Pumps (UK) — worldpumps.com — tech features

Modern Pumping Today (US) — modernpumpingtoday.com — guest articles

Empowering Pumps & Equipment (US) — empoweringpumps.com — thought leadership

Engineering & Technology / IET (UK) — eandt.theiet.org — features

Manufacturing Today (UK) — manufacturing-today.com — supplier features

The Manufacturer (UK) — themanufacturer.com — editorials

Process Engineering (UK) — processengineering.co.uk — technical articles

Thomas Insights (US) — blog.thomasnet.com — sourcing thought leadership

Sample pitch (use for ALL): Subject: Contributed article — 'How Indian Tube Manufacturers Meet ASTM A312 for US Pump OEMs'. Body: (1) intro Apurvi credentials — ISO 9001, EN 10204 3.1 MTC, 25–200 HP specialization; (2) three article angles; (3) word count + delivery date; (4) author bio linking to apurviind.com.

## Tier 3 — Reddit / Quora / Stack Exchange

Reddit rule of engagement: 10 helpful comments before any link drop. Always disclose 'I work at a stainless tube manufacturer in India'. Tailor every response. Throwaway karma-building period of 2 weeks first.

r/AskEngineers (1.4M) — 304L vs 316L for pump applications, PREN explained

r/Welding (350K) — TIG welding ASTM A312 tubes, butt-weld vs socket-weld

r/MetalManufacturing (25K) — Cold-drawn vs hot-rolled tube manufacturing

r/Manufacturing (200K) — India manufacturing capabilities deep-dives

r/Plumbing (800K) — Stainless vs galvanized for industrial water lines

r/Procurement (60K) — What buyers should ask Indian suppliers

r/SmallBusiness (2M) — Case study: 'How we landed a US distributor'

r/IndianBusiness — Export documentation, MTC compliance, FOB pricing

## Tier 4 — HARO / Featured.com / Qwoted (10 ready angles)

China+1 winners — concrete US buyer shift to India

Aluminum supply chain — 6061/6063 for US fuel infrastructure

EV charging vs vapor recovery demand

Indian MSME export success story

EN 10204 3.1 MTC explainer

Welding certifications India vs Europe

Sustainable / recycled stainless steel content

Lead-time benchmarks: India 4–6 wk vs China 8–12 wk

Family-owned manufacturer story (founder Viren Gathani)

Section 232 tariff impact on industrial buyers

Featured.com — featured.com — daily expert queries

Qwoted — qwoted.com — highest HARO-alt conversion

Source of Sources — sourceofsources.com — Peter Shankman successor

ResponseSource UK — responsesource.com — UK journalist requests

#JournoRequest on X — Fastest response window

## Tier 5 — LinkedIn (founder + company)

Cadence — 5 founder posts/week + 1 LinkedIn Article every 2 weeks

LinkedIn Newsletter — 'Tubing Talk: Inside Industrial Steel Manufacturing' — biweekly, 1,000–1,500 words

Sales Navigator — 30 connect requests/day to US/UK Procurement Managers, Plant Engineers, Pump OEM Sourcing Heads

Showcase Pages — One per product line (Motor Tubes / Vapour Tubing / Pump Sleeves) — each separately indexable

Hashtag mix — 3 broad (#manufacturing #stainlesssteel #B2B) + 3 niche (#ASTMA312 #vaporrecovery #pumpcomponents) + 3 geo (#USmanufacturing #UKindustry)

## Tier 6 — Strategic partnerships (5–8 in 30 days)

US/UK pump OEM channel partners (Grundfos, Franklin Electric, Pentair, Xylem distributors)

Gas station equipment distributors (OPW, Gilbarco, Fairbanks Pumps UK)

Water treatment integrators (Evoqua, Veolia US, Severn Trent suppliers UK)

Pump rebuild / repair shops (regional US/UK)

Trade associations (BSSA UK, Hydraulic Institute US, BPMA UK)

Procurement marketplaces (Scoutbee, Tealbook supplier discovery)

# 5. Paid Campaign Layer — $8–10K to Bridge the Impression Gap

| Channel | Budget (USD/mo) | Impressions | Why |
| --- | --- | --- | --- |
| Google Search (US+UK, high-intent only) | $2,500 | ~40K | Highest-intent B2B |
| Bing Ads (US, Copilot inventory) | $1,500 | ~50K | BEST ROI in 2026 — Copilot is 35-40% of US B2B; CPC 33-40% cheaper |
| LinkedIn Ads (procurement titles) | $2,500 | ~50K | Highest B2B precision |
| Reddit Ads (r/Welding, r/AskEngineers) | $800 | ~80K | Cheap, niche-targeted |
| YouTube TrueView (factory tour 15s) | $1,000 | ~80K | Brand storytelling |
| Google Display (industrial whitelist) | $400 | ~100K | Cheap vanity impressions |
| Quora Ads | $300 | ~40K | Long-tail buyer questions |
| TOTAL | $9,000 | ~440K |  |

Lean alternative: $3,500/mo (GDN + Reddit + Bing only) = ~300K vanity impressions. Use only if budget is tight and lead quality is acceptable.

## Paid risk caveats

Industrial/manufacturing flag — submit business verification on Day 1

Geo-exclude India / Pakistan / Bangladesh from US/UK campaigns

Frequency cap on Display + YouTube — prevent CPM inflation

LinkedIn CPM up 15% YoY — lock budget early-month

# 6. Competitor Teardown — Who to Leapfrog

## US Top 10

| # | Domain | HQ | Type | DA | Strength |
| --- | --- | --- | --- | --- | --- |
| 1 | pennstainless.com | Quakertown, PA | Mill-tier distributor | 50–55 | Deep technical content; ranks #1 on most A312 long-tails |
| 2 | continentalsteel.com | Fort Lauderdale, FL | Distributor | 55–60 | Largest content moat |
| 3 | plymouth.com (Plymouth Tube) | Warrenville, IL | Manufacturer (5 US mills) | 50–55 | True manufacturer credentials |
| 4 | twmetals.com | Exton, PA | Distributor | 55 | Strong rich-snippet game |
| 5 | usmetals.com | Houston, TX | Distributor | 40–45 | Oil & gas vertical |
| 6 | atlassteel.com | Twinsburg, OH | Manufacturer | 35–40 | Owns A268-specific ranking |
| 7 | eagletube.com | Trevose, PA | Mfr/processor | 35 | Process-led pages |
| 8 | worldwidepipe.com | Houston, TX | Distributor | 35–40 | OCTG link equity |
| 9 | stainlessandalloy.com | Statham, GA | Distributor | 30 | Lean, fast |
| 10 | opwglobal.com | Hodgkins, IL | Mfr | 65–70 | Owns EPA Stage I/II vapor SERP |

## UK Top 10

| # | Domain | HQ | Type | DA | Strength |
| --- | --- | --- | --- | --- | --- |
| 1 | aalco.co.uk | Surrey | Multi-metal stockist (18 centres) | 50–55 | Owns 'stainless steel tube UK' |
| 2 | marcegaglia.co.uk | West Midlands | Manufacturer (largest UK) | 55 | Manufacturer + scale |
| 3 | smithmetal.com | Bedfordshire | Stockholder + UKAS lab | 45–50 | UKAS lab = compliance trust |
| 4 | materials.sandvik (UK) | Sheffield | Manufacturer | 80+ | Brand authority |
| 5 | outokumpu.com (UK) | Sheffield | Manufacturer | 65 | Coil/long products |
| 6 | steelexpress.co.uk | Wolverhampton | Stockist | 35–40 | Wins seamless tube UK |
| 7 | themetalstore.co.uk | Manchester | Online retailer | 35–40 | E-commerce UX |
| 8 | stainlessandaluminium.co.uk | Tipton | Stockist | 25–30 | Page-per-grade |
| 9 | nero.co.uk | Bristol | Pipe fitting stockist | 30–35 | Same-day dispatch |
| 10 | bssa.org.uk | Sheffield | Trade body | 55 | Top-3 for EN 10296-2 — must-target backlink |

## Content gaps Apurvi can win (zero/weak competitor coverage)

EN 10204 3.1 MTC walkthrough for US buyers — competitors mention it; none explain it

ASTM A268 vs A269 vs A312 full comparison matrix — nobody has it

India vs China stainless steel sourcing 2026 — zero competitor content

How US procurement qualifies an Indian SS tube manufacturer — buyer-journey gap

Submersible pump motor shell material selection (304 vs 316 vs duplex) — pump OEMs don't publish; tube suppliers don't either

Aluminum vapor-recovery rigid tubing — Stage I balance retrofit (OPW sells systems, nobody owns the tubing replacement-part SERP)

EN 10296-2 vs ASTM A554 dimensional tolerance comparison

High HP submersible pump tube — 50/75/100 HP shell sizing (pure long-tail Apurvi can sweep)

Section 232 + duty-drawback for Indian exporters — timely, pulls procurement buyers

NRV (non-return valve) sizing chart for submersible pump risers — English-language version doesn't exist well

## The one weakness every Indian exporter has — and how Apurvi sidesteps it

Common weakness: Indian exporter sites read like Indian-domestic sites: no US/UK phone, no local addresses, no US testimonials, MTCs buried, IndiaMART-only backlinks, WhatsApp-only contact, INR pricing.

Get a US 1-800 + UK 0800 forwarding number

Set up US Inc / UK Ltd shell or registered-agent address (drop-shipping/forwarder OK)

Build /us/ and /uk/ subfolders with hreflang (NOT subdomains)

Pin SGS / Bureau Veritas / TUV inspection logos in the hero of every product page

Host 2–3 US case studies as soon as orders close — even small ones

Embed sample MTC PDF (anonymized) on every grade page

Get listed on Thomasnet — single highest-ROI US B2B backlink

Avoid 'manufacturer in India' in /us/ titles — write 'ASTM A312 TP304 supplier — MTC 3.1 certified, USA delivery'

Reference Section 232 reality on every US page — '~20–30% landed-cost advantage vs Chinese-origin'

Replace WhatsApp-only with Calendly link for sales calls

# 7. The 30-Day Calendar (Day-by-Day)

## Week 1 (29 Jun – 5 Jul) — Foundation + Indexing

| Day | Task |
| --- | --- |
| 1 | Ship on-site code: hreflang fix, robots.txt update, llms-full.txt, US/UK schema (DONE — see tech brief) |
| 1 | Submit apurviind.com to Bing Webmaster Tools. Verify Domain in GSC. |
| 1 | Create skeleton /us/ and /uk/ folders (homepage + products + contact) |
| 2 | Submit sitemaps for /us/ and /uk/ to GSC + Bing. Ping IndexNow. |
| 2 | Apply for DUNS (D&B Hoovers — 30-day issuance) |
| 2 | Sign up US 1-800 + UK 0800 forwarding (Twilio / OpenPhone / Voipfone) |
| 3 | List on ThomasNet, GlobalSpec, Kompass US, Kompass UK, Europages |
| 3 | Launch paid accounts: Google, Bing, LinkedIn, Reddit, YouTube. Submit business verification. |
| 4 | Publish blog #1: SS 304 vs 316 for Submersible Pump Motor Tubes |
| 4 | List on Applegate, DirectIndustry, Manta, MFG.com, AZoM |
| 5 | Publish blog #2: ASTM A312 vs A213 vs A268 |
| 5 | Author bios live for Viren Gathani + senior engineer (E-E-A-T) |
| 6 | Publish blog #3: EN 10204 Type 3.1 MTC Explained + Lead Magnet #2 ships (MTC PDF) |
| 6 | LinkedIn Article #1 published by founder. Cross-post to Medium with canonical. |
| 7 | YouTube short #1: factory tour (60s, ASTM mark visible). Embed in homepage. |
| 7 | First Reddit answers in r/AskEngineers (10 helpful comments, zero links) |

## Week 2 (6 Jul – 12 Jul) — Vapour Recovery + Compliance

| Day | Task |
| --- | --- |
| 8 | Publish blog #5: Stage II Vapour Recovery Decommissioning + LinkedIn |
| 8 | Launch paid campaigns LIVE — Google + Bing + Reddit + LinkedIn + Display |
| 9 | Publish blog #6: Al 6061 vs 6063 vs 5052 for Petrol Vapour Lines |
| 10 | Publish Pillar B (3,500 words): Aluminum Vapour Recovery Tubing Compliance Guide |
| 10 | Pitch posts #5 + #8 to NACS Magazine, Convenience Store News, Petrol Plaza |
| 11 | Publish blog #8: UK PPC Vapour Recovery Compliance |
| 11 | Lead Magnet #4 ships: Vapour Recovery Compliance Map (US state + UK region) |
| 12 | Reddit answers across r/Welding, r/MetalManufacturing |
| 13 | LinkedIn Article #2 by founder: China+1 — What US Procurement Is Doing in 2026 |
| 14 | YouTube short #2: Aluminum vapour tubing close-up + EXIF metadata |

## Week 3 (13 Jul – 19 Jul) — Trust + Sourcing

| Day | Task |
| --- | --- |
| 15 | Publish blog #7 (Pillar C kickoff): Sourcing SS Pipes from India — 12-Point Audit |
| 16 | Publish blog #10: How to Spot a Fake MTC (5 Red Flags) |
| 17 | Publish blog #12: Section 232 + CBAM 2026 — Real Landed Cost |
| 17 | Lead Magnet #7 ships: 12-Point Supplier Audit Checklist |
| 18 | Lead Magnet #5 ships: Indian SS Pipe Landed-Cost Calculator |
| 19 | Publish Pillar C (3,500 words) |
| 20 | First HARO/Featured.com pitches (5 angles) |
| 21 | LinkedIn Newsletter #1 launches: 'Tubing Talk' inaugural issue |

## Week 4 (20 Jul – 28 Jul) — Spec Depth + Long-Tail Sweep

| Day | Task |
| --- | --- |
| 22 | Publish blog #4: 4″/6″/8″ Sizing Chart + Lead Magnet #1 ships (Pump-Tube Sizing Calculator) |
| 22 | Outreach to 30 pump distributors offering Calculator embed widget |
| 23 | Publish blog #9: Higher HP (15–50 HP) Deep-Well Motor Tubes |
| 24 | Publish blog #11 + #13 spec sheet day |
| 25 | Publish Pillar A (3,500 words) |
| 26 | YouTube shorts #3 + #4: MTC walkthrough + 4″/6″/8″ animation |
| 27 | Audit AI Overview appearances using Otterly/Profound. Tweak underperforming posts. |
| 28 | LinkedIn Article #3 by founder + LinkedIn Newsletter #2 |
| 29 | Final HARO/Featured submissions |
| 30 | Generate monthly report: GSC impressions split US/UK + Bing AI Performance + RFQ count |

## Daily operations (every day, ~30 min)

10 LinkedIn comments on procurement/engineering posts

2 Reddit helpful answers (karma building)

1 Quora answer

Track citations in ChatGPT / Perplexity / AIO via Otterly or Profound

# 8. KPI Dashboard (track weekly)

| Metric | Vanity? | Target Month 1 |
| --- | --- | --- |
| Total search impressions (GSC US + UK split) | Partial | 250K–400K |
| AI Overview / Bing Copilot citations | No | 8–15 (Bing WMT AI Performance) |
| Organic clicks (US + UK) | No | 4,000–8,000 |
| Qualified RFQs from US/UK IPs | PRIMARY | 30 |
| Cost per qualified RFQ | No | < $400 |
| Brand search volume (WoW growth) | No | +30% |
| Referring domains (US/UK origin) | No | +15 new |
| LinkedIn Article impressions | Partial | 30K |
| YouTube view-through (15s+) | Partial | 8K |
| Newsletter / MTC sample downloads | No | 200 |
| Pump-Tube Sizing Calculator embeds (3rd-party) | No | 5 |

Cardinal rule: 400K impressions with < 20 qualified RFQs = failed campaign. Pivot if that ratio breaks at week 2.

# 9. Off-Site Action List (Owner: SEO + Marketing Team)

| Action | Day | Critical? |
| --- | --- | --- |
| Bing Webmaster Tools verification + sitemap | Day 1 | CRITICAL |
| Google Search Console — verify Domain property + sitemap | Day 1 | CRITICAL |
| Apply for D&B DUNS number | Day 2 | CRITICAL (30-day issuance) |
| US 1-800 + UK 0800 forwarding numbers | Day 2 | CRITICAL |
| ThomasNet listing (business.thomasnet.com/get-listed-on-thomasnet) | Day 3 | CRITICAL |
| Kompass US + UK listings | Day 3 | HIGH |
| Europages + Applegate UK listings | Day 4 | HIGH |
| GlobalSpec / Engineering360 supplier profile | Day 4 | HIGH |
| Launch Google + Bing + LinkedIn + Reddit Ads accounts; business verification | Day 3 | CRITICAL |
| ISO 9001 + SGS / TUV / BV logos sourced and added to product pages | Day 5 | CRITICAL US trust |
| Founder LinkedIn refresh (Viren Gathani — photo, banner, headline) | Day 5 | HIGH |
| Sign up for Featured.com / Qwoted / SOS / ResponseSource UK | Day 6 | HIGH |
| BSSA membership application (UK trade body) | Week 2 | MEDIUM |
| LinkedIn Sales Navigator subscription | Week 1 | HIGH |
| 2–3 US/UK customer testimonials sourced + photos | Week 2 | CRITICAL |
| Calendly for sales calls (replace WhatsApp-only) | Day 5 | CRITICAL |
| ISSF + ISSDA + BSSA membership listings | Week 2 | MEDIUM |
| 3 monthly LinkedIn Articles by founder | Ongoing | HIGH |

# 10. Risk Register

| Risk | Mitigation |
| --- | --- |
| Indexing delays (new pages stuck 14–30 days) | IndexNow ping every publish + internal linking from existing 16 pages + GSC URL Inspection API |
| Paid account suspension (industrial flagged) | Submit business verification Day 1; clean landing pages; no exaggerated claims |
| AI Overview click cannibalization (-39% CTR at pos 2) | Optimize for BEING cited in AI Overviews — structured data, factual specs, comparison tables |
| Manual penalty from spammy directory listings | Tier 1 directories only (no bulk submissions) |
| Google spam updates (Aug/Mar cadence) | Stick to deep technical content; avoid thin AI-generated pages |
| LinkedIn CPM inflation | Lock budget early-month, watch frequency caps |
| Hreflang misconfiguration | Self-reference canonical on every locale; bidirectional alternates |
| Wrong-country impressions | Geo-exclude India / Pakistan / Bangladesh in US/UK ad sets |
| Vanity 400K with no leads | Track qualified RFQs as PRIMARY metric — pivot at week 2 if ratio breaks |

# 11. Month 2 and Beyond

600K–1M impressions (paid amortizes, organic compounds)

80+ qualified RFQs

5+ podcast appearances on industrial/procurement shows

First US/UK case study published

Pump-Tube Sizing Calculator → 30+ 3rd-party embeds

BSSA / Hydraulic Institute / BPMA memberships finalised

By month 6: top-10 ranking on Google US for at least 5 mid-tail keywords + weekly Perplexity/ChatGPT citations for 'non-China stainless tube supplier' type queries